## 1. Team
Team Member | Role in Team | Rules | Scrum Values
Michelle Rasebotsa | Dev | Collaborate respectfully | Courage
Elias Kekana | Scrum Master (+Dev) | Be punctual | Focus
Lerato Phetle | Dev | Be open about impediments | Commitment
Luthando Jayiya | Product Owner (+Dev) | Have a learning mindset | Respect
Openness
Product Goal |  | Definition of Done
To develop a banking application that allows for the creation, management and tracking of various types of bank accounts and customer information. |  | When a minimum Viable product has been producted for the system. (Customer, Bank Staff and Admin Mode)

## 2. Product Vision
Front Side | Back Side
MELLBANK | The bank design system will be used to generate and organise data for a bank. We want to create, manage, and track different types of bank accounts, customer information, and the connections between accounts and customers.
Logo | Account Management • Create, update, and close savings and current accounts for customers. • View a list of all available accounts and their balances. • Set and update the interest rate for savings and current accounts. • Withdraw and deposit funds in customer accounts. • Maintain a transaction history for all accounts. Customer Management • View a list of all customers. • View detailed customer information. • Add new customers and update existing customer information. • Delete customers from the system. User Management • Register new users and generate emails with credentials. • Update user information and delete users. • View and update user profiles. • View personal profiles and update profile information. Administrative Features • Generate and send emails with credentials to customers after registration. • Ensure efficient and responsive system performance. • Maintain data integrity and security throughout all operations.
• Security: Robust security measures to protect personal information • Convenience: Offer convenient ways for customer's to make transactions • Interest Rates: Competitive interest rates on saving accounts | • Individuals and businesses • Require internet access.

## 3. Measures of Success
Features | Criteria
Admin Mode | • Can create savings/current accounts for customers • Can update savings/current acccounts for customers • Can close savings/current accounts • Can view list of available accounts • Can View a list of customers • Can view customer information • Can add new customer • Can update customer • Can delete customer • Can view transaction history • Can set/update the interest rate for savings/current accounts • Can add new user by registering them • Can update user information • Can delete user • Can view my profile • Can update my profile • Generate email with credentials to customer after registration
Bank Staff Mode | • Can create savings/current accounts for customers • Can update savings/current acccounts for customers • Can view list of available accounts • Can View a list of customers • Can view customer information • Can add new customer • Can update customer • Can view transaction history • Can set/update the interest rate for savings/current accounts • Can view my profile • Can update my profile • Generate email with credentials to customer after registration
Customer Mode | • View Account balances and all available accounts • Can Withdraw amount • Can Deposit amount • Can Update their Information • Can view transaction history • Can view my profile • Can update my profile

## 4. Stakeholder Diagram
Jabu(University Graduate)
Characteristics | Goals
• Recent graduate | • Travel to 50 different countries
• Interested in saving money | • Save up for the future
• Hardworking and likes to travel | • Have five streams of income
• Just started working | • Wants to buy his family a house
Likes | Dislikes
• Convenient banking systems | • High fees and bank charges
• Traveling to different countries | • Complicated bank processes
• Trying out different restaurants | • Poor customer service
Sipho(Admin)
Characteristics | Goals
• Admin at MELL Bank | • Aims to ensure that the bank application runs smoothly
• Good with various software | • Improve productivity in the company
• Detail oriented | • Continuous improvement of the banking system
• Works well with the development team | • Find more ways to make the system easier to use
Likes | Dislikes
• Automate systems and save time | • Going outdoors; they would rather sit inside and manage their accounts indoors.
• Organise their lives in a sequential way | • Complicated bank processes
• Visualise their own data | • Customer service challenges
Sindi(Bank Staff)
Characteristics | Goals
• Bank consultant with 15 years experience | • Aims to give the best customer service
• Highly panctual and organised | • Cross-sell other bank products and services
• Analytical minded | • Aspires to have 30 years experience as a bank consultant.
• Reliable | • Wants to learn how the banking system works at a technical level.
Likes | Dislikes
• Like math puzzles | • Dislikes seeing customers frustrated by long wait times
• Enjoys assisting customers with their banking needs | • Rude customers
• Fast and efficient systems | • Slow and inefficient systems that hinder productivity
MELL
BANK
FDM Trainers
University Graduate
Bank Staff
Business owner
Admin

## 5.3 UI Flow Diagram
Customer UI Flow Diagram |  | Admin UI Flow Diagram
Bank Staff UI Diagram

## 6.1 User Stories
User Stories
Admininistrator
As an Admin, I want to log into the system, so that I can view the Admin homepage.
As an Admin, I want to see the admin homepage, so that I can access and manage the administrative functions
As an Admin, I want to view all customers, so that I can oversee and manage customer information
As an Admin, I want to add a new customer, so that I can give access to new customers.
As an Admin, I want to update customer information, so that I can keep customer information up to date.
As an Admin, I want to delete customer users, so that I can control access to the system.
As an Admin, I want to view all users of the system, so that I can manage access information.
As an Admin, I want to view all bank staff, so that I can oversee and manage bank staff information.
As an Admin, I want to add new bank staff, so that I can grant access to the system.
As an Admin, I want to update bank staff information, so that I can keep it up to date.
As an Admin, I want do delete bank staff user's, so that I can control access to the system.
As an Admin, I want to view all accounts, so that I can manage bank account information.
As an Admin, I want to create a savings account for a customer, so that I can grant them access to a savings account.
As an Admin, I want to create a current account for a customer, so that I can grant them access to a current account.
As an Admin, I want to update savings accounts, so that I can keep it up to date.
As an Admin I want to update current accounts, so that I can keep it up to date.
As an Admin, I want to delete a savings account, so that I can deactivate it.
As an Admin, I want to delete a current account, so that I can deactivate it.
As an Admin, I want to mantain a transaction history for each account, so that I can display it to the customer.
As an Admin, I want to send notifications to customers, so that I can keep them informed.
As an Admin, I want to set an overdraft for a current account, so that a customer can take advantage of it.
As an Admin, I want to logout of the system, so that I can end my shift.
Bank Staff
As a Bank Staff, I want to log into the system, so that I can see the Bank Staff homepage.
As a Bank Staff, I want to see the Bank Staff homepage, so that I can manage accounts and customer information.
As a Bank Staff, I want to add a new customer, so that I can register new clients in the banking system.
As a Bank Staff, I want to open savings accounts for customers, so that I can give them access to savings account services.
As a Bank Staff, I want to open current account for customers, so that I can give them access to current account services.
As a Bank Staff, I want to view all bank accounts that belong to a customer, so that I can assist them with their queries.
As a Bank Staff, I want to update the interest rate on savings accounts, so that I can keep the account balance accurate.
As a Bank Staff, I want to create a current account without an overdraft amount and interest charge rate, so that I can manage accounts.
As a Bank Staff, I want to create a current account with an overdraft amount and interest charge rate, so that I can manage provide overdraft services to customers.
As a Bank Staff, I want to update overdraft amounts, so that I can manage overdraft charges.
As a Bank Staff, I want to update overdraft interest rate amounts, so that I can manage overdraft interest rate charges.
As a Bank Staff, I want to view the transaction history of an account, so that I can provide a detailed account statement to the customer.
As a Bank Staff, I want to logout of the system, so that I can end my shift.
Customer
As a Customer, I want to log into the system, so that I can access the customer homepage.
As a Customer, I want to see the customer homepage, so that I can access my accounts, profile, and banking services.
As a Customer, I want to view my balance, so that I can manage my finances effectively.
As a Customer, I want to see my accounts, so that I can perform transactions.
As a Customer, I want to withdraw money from my savings account, so that I can access my money when I need it.
As a Customer, I want to withdraw money from my current account, so that I can access my money when I need it.
As a Customer, I want to deposit money into my savings account, so that I manage and save my money.
As a Customer, I want to deposit money into my current account, so that I manage and save my money.
As a Customer, I want to view the transaction history of my accounts, so that I can track my withdrawals and deposits.
As a Customer, I want to update my information, so that I can keep it up to date.
As a Customer, I want to receive notifications about my account activities or changes, so that I am always informed about my banking status.
As a Customer, I want to logout of the system, so that I can keep my information secure.

## 6.2 Product Backlog
No. | Product Backlog | Category | Type | Story points | Priority | Short Description
1 | As an Admin, I want to log into the system, so that I can view the Admin homepage. | Admin | Functional | 2 | 1 | Admin Login functionality
2 | As an admin, I want to logout of the system, so that I can end my shift. | Admin | Functional | 1 | 2 | Admin logout functionality
3 | As an Admin, I want to see the admin homepage, so that I can access and manage the administrative functions | Admin | Functional | 5 | 3 | Admin homepage display
4 | As an Admin, I want to view all customers, so that I can oversee and manage customer information | Admin | Functional | 1 | 4 | Admin view customer list
5 | As an Admin, I want to add a new customer, so that I can give access to new customers. | Admin | Functional | 3 | 5 | Admin adding new customers
6 | As an Admin, I want to update customer information, so that I can keep customer information up to date. | Admin | Functional | 5 | 1 | Admin updating customer information
7 | As an Admin, I want to delete customer users, so that I can control access to the system. | Admin | Functional | 1 | 2 | Admin deleting a customer record
8 | As a Customer, I want to log into the system, so that I can access the customer homepage. | Customer | Functional | 2 | 1 | Customer Login functionality
9 | As a Customer, I want to logout of the system, so that I can keep my information secure. | Customer | Functional | 1 | 2 | Customer Logout functionality
10 | As a Customer, I want to view my balance, so that I can manage my finances effectively. | Customer | Functional | 1 | 3 | Customer viewing balance
11 | As a Customer, I want to see my accounts, so that I can perform transactions. | Customer | Functional | 2 | 4 | View my accounts
12 | As a Customer, I want to withdraw money from my savings account, so that I can access my money when I need it. | Customer | Functional | 3 | 5 | Customer withdraw money from savings account
13 | As a Customer, I want to withdraw money from my current account, so that I can access my money when I need it. | Customer | Functional | 3 | 1 | Customer withdraw money from current account
14 | As a Customer, I want to deposit money into my savings account, so that I manage and save my money. | Customer | Functional | 3 | 2 | Customer depositing money into savings account
15 | As a Customer, I want to deposit money into my current account, so that I manage and save my money. | Customer | Functional | 3 | 3 | Customer depositing money into current account
16 | As a Customer, I want to see the customer homepage, so that I can access my accounts, profile, and banking services. | Customer | Functional | 3 | 4 | View customer homepage
17 | As a Bank Staff, I want to log into the system, so that I can see the Bank Staff homepage. | BankStaff | Functional | 2 | 1 | Bank Staff Login functionality
18 | As a Bank Staff, I want to logout of the system, so that I can end my shift. | BankStaff | Functional | 1 | 2 | Bank Staff Logout functionality
19 | As a Bank Staff, I want to see the Bank Staff homepage, so that I can manage accounts and customer information. | BankStaff | Functional | 3 | 3 | Bank Staff homepage display
20 | As a Bank Staff, I want to add a new customer, so that I can register new clients in the banking system. | BankStaff | Functional | 3 | 4 | Bank Staff adding new customers
21 | As an Admin, I want to view all users of the system, so that I can manage access information. | Admin | Functional | 2 | 1 | View all user accounts
22 | As an Admin, I want to view all accounts, so that I can manage bank account information. | Admin | Functional | 2 | 2 | View all accounts
23 | As an Admin, I want to create a savings account for a customer, so that I can grant them access to a savings account. | Admin | Functional | 5 | 3 | Open a savings account
24 | As an Admin, I want to create a current account for a a customer, so that I can grant them access to a current account. | Admin | Functional | 8 | 4 | Open a current account
25 | As an Admin, I want to update savings accounts, so that I can keep it up to date. | Admin | Functional | 5 | 5 | Update savings account
26 | As an admin I want to update current accounts, so that I can keep it up to date. | Admin | Functional | 2 | 1 | Update current account
27 | As an Admin, I want to delete a savings account, so that I can deactivate it. | Admin | Functional | 1 | 2 | Delete savings account
28 | As an admin, I want to delete a current account, so that I can deactivate it. | Admin | Functional | 1 | 3 | Delete current account
29 | As a Customer, I want to view the transaction history of my accounts, so that I can track my withdrawals and deposits. | Customer | Functional | 3 | 1 | View my transaction history
30 | As a Customer, I want to update my information, so that I can keep it up to date. | Customer | Functional | 3 | 2 | Update my information
31 | As a Customer, I want to receive notifications about my account activities or changes, so that I am always informed about my banking status. | Customer | Functional | 3 | 3 | Receive notifications
32 | As an Admin, I want to mantain a transaction history for each account, so that I can display it to the customer. | Admin | Functional | 5 | 1 | Admin
33 | As an Admin, I want to send notifications to customers, so that I can keep them informed. | Admin | Functional | 5 | 2 | Admin
34 | As an Admin, I want to view all users of the system, so that I can manage access information. | Admin | Functional | 2 | 3 | Admin
35 | As a Bank Staff, I want to open savings accounts for customers, so that I can give them access to savings account services. | BankStaff | Functional | 5 | 1 | Open savings account
36 | As a Bank Staff, I want to open current account for customers, so that I can give them access to current account services. | BankStaff | Functional | 8 | 2 | Open current account
37 | As a Bank Staff, I want to view all bank accounts that belong to a customer, so that I can assist them with their queries. | BankStaff | Functional | 3 | 3 | View bank accounts of customer
38 | As a Bank Staff, I want to update the interest rate on savings accounts, so that I can keep the account balance accurate. | BankStaff | Functional | 5 | 4 | update/set interest rate for savings accounts
39 | As a Bank Staff, I want to create a current account without an overdraft amount and interest charge rate, so that I can manage accounts. | BankStaff | Functional | 5 | 5 | Create current account without overdraft
40 | As a Bank Staff, I want to create a current account with an overdraft amount and interest charge rate, so that I can manage provide overdraft services to customers. | BankStaff | Functional | 5 | 1 | Create current with overdraft
41 | As a Bank Staff, I want to update overdraft amounts, so that I can manage overdraft charges. | BankStaff | Functional | 5 | 2 | Update/set overdraft amount
42 | As a Bank Staff, I want to update overdraft interest rate amounts, so that I can manage overdraft interest rate charges. | BankStaff | Functional | 5 | 3 | Update/set overdraft interest rate
43 | As a Bank Staff, I want to view the transaction history of an account, so that I can provide a detailed account statement to the customer. | BankStaff | Functional | 5 | 4 | View transaction history of an account
44 | As an Admin, I want to view all bank staff, so that I can oversee and manage bank staff information. | Admin | Functional | 2 | 1 | View bank staff
45 | As an Admin, I want to add new bank staff, so that I can grant access to the system. | Admin | Functional | 5 | 2 | add new bank staff
46 | As an Admin, I want to update bank staff information, so that I can keep it up to date. | Admin | Functional | 4 | 3 | Update bank staff details
47 | As an Admin, I want do delete bank staff user's, so that I can control access to the system. | Admin | Functional | 1 | 4 | delete bank staff
48 | As a Bank Staff, I want to guarantee customer confidentiality, so that I can assure them their information is safe. | BankStaff | Non-Functional | 8 | 1 | Confidentiality for access to system information
49 | As a Customer, I want a smooth user experience in a bank system, so that I can easily do my banking | Customer | Non-Functional | 5 | 2 | Smooth user experience
50 | As an Admin, I want to use an efficient system, so i can be productive | Admin | Non-Functional | 3 | 1 | Reliable and efficient system
51 | As a bank staff, I want to see a well organized homepage after logging in, so that i can easily navigate to manage accounts and customer information | BankStaff | Non-Functional | 3 | 2 | Great user experience

## 7. Velocity and Sprint Backlog
No. | Product Backlog | Time Estimate | Bucket Size | Type | Priorities |  |  | Sprint 1 Backlog
1 | Create requirements document | medium | 3 | Functional | 1 | Sprint Length | 2 weeks | 1 | Create requirements document
2 | Setup Projects for collaboration | med-large | 5 | Functional | 1 | Max Velocity per Sprint | 24 | 2 | Setup Projects for collaboration
3 | Create ERD Diagram | medium | 3 | Functional | 2 | Product Backlog | 113 | 3 | Create ERD Diagram
4 | Make Entity Framework sample data | medium | 3 | Functional | 3 | Total Sprints | 3 | 4 | Make Entity Framework sample data
5 | Setting up REST API endpoints | med-large | 5 | Functional | 3 |  |  | 5 | Setting up REST API endpoints
6 | Log-in functionality web api | small | 2 | Functional | 1 |  |  | 6 | Log-in functionality web api
7 | UI Design & Wireframes | med-large | 5 | Functional | 4 |  |  | 7 | Wireframes
8 | Log-In functionality front end | medium | 3 | Functional | 1 | Team Velocity |  | 8 | Log-In functionality
9 | View Admin homepage | med-large | 5 | Functional | 2 | MMR | 2 | 9 | Robust authorization and authentication
10 | View Bank Staff homepage | medium | 3 | Functional | 3 | LP | 2 | 10 | Update a customer
11 | View Customer homepage | medium | 3 | Functional | 4 | EK | 3 | 11 | Delete current account
12 | View List of customers | smaller | 1 | Functional | 5 | LJ | 5 | 12 | View Admin homepage
13 | Add new customer | medium | 3 | Functional | 5 |  |  | 13 | Delete a customer
14 | View customer details | small | 2 | Functional | 5 | Priorities |  | 14 | Open current account
15 | Update a customer | med-large | 5 | Functional | 1 | High | 1 | 15 | View Bank Staff homepage
16 | Delete a customer | smaller | 1 | Functional | 2 | Medium-High | 2 | 16 | Deposit functionality
17 | Open current account | large | 8 | Functional | 3 | Medium | 3 | 17 | Add a new user
18 | Open savings account | med-large | 5 | Functional | 4 | Medium-Low | 4 | 18 | Open savings account
19 | View List of Accounts | small | 2 | Functional | 5 | Low | 5 | 19 | View Customer homepage
20 | View account details | small | 2 | Functional | 5 |  |  | 20 | Withdraw functionality
21 | View balance | smaller | 1 | Functional | 5 |  |  | 21 | View user details
22 | Update account details | medium | 3 | Functional | 5 | Bucket Size |  | 22 | View list of users
23 | Delete current account | med-large | 5 | Functional | 1 | smaller | 1 | 23 | Add new customer
24 | Delete savings customer | med-large | 5 | Functional | 2 | small | 2 | 24 | Update account details
25 | Deposit functionality | medium | 3 | Functional | 3 | medium | 3 | 25 | View my transaction history
26 | Withdraw functionality | medium | 3 | Functional | 4 | med-large | 5 | 26 | View customer details
27 | View List of my accounts | small | 2 | Functional | 5 | large | 8 | 27 | View List of Accounts
28 | View details of my account | small | 2 | Functional | 5 |  |  | 28 | View account details
29 | View my transaction history | medium | 3 | Functional | 5 |  |  | 29 | View List of my accounts
30 | Add a new user | large | 8 | Functional | 3 |  |  | 30 | View details of my account
31 | View List of Users | small | 2 | Functional | 3 |  |  | 31 | View List of customers
32 | View user details | small | 2 | Functional | 4
33 | Update user details | medium | 3 | Functional | 4
34 | Delete user | small | 2 | Functional | 5
35 | View total of my bank balance | small | 2 | Functional | 5
36 | View transactions made | med-large | 5 | Functional | 5
37 | Robust authorization and authentication | large | 8 | Non-Functional | 1 |  |  |  | Sprint 2 Backlog
38 | Accessibility with text to speech | medium | 3 | Non-Functional | 2 |  |  | 1 | Implement notification system
39 | Smooth & efficient user experience | medium | 3 | Non-Functional | 3 |  |  | 2 | Send automatic email to customer
40 | Confidentiality for access to system information | med-large | 5 | Non-Functional | 3 |  |  | 3 | Generate bank statements (In account details)
[8 empty] | 4 | Two factor authentication to improve security
[8 empty] | 5 | Allow user to link multiple user accounts
[8 empty] | 6 | Add analytics and reports (In account details)
[8 empty] | 7 | Manage bank account daily limits
Sprint 3 Backlog
[8 empty] | 1 | Allow online purchases (e.g airtime, electricity)
[8 empty] | 2 | Allow customers to apply for loans and credit cards
[8 empty] | 3 | Allow customers to view credit status
[8 empty] | 4 | Allow customer to book an appointment with a financial adviser
[8 empty] | 5 | Allow customers to transfer money from one account to another
[8 empty] | 6 | Allow customer to make a facade bank account (for security purposes)
[8 empty] | 7 | Allow customer's to set debit orders

## 8. Project Plan
Product Goal
To develop a banking application that allows for the creation, management and tracking of various types of bank accounts and customer information.
Product Backlog | Priorities | Bucket Size | Time Estimated (hours) | Assigned Team | Sprint 1 |  |  | Sprint Size: | 118
Robust authorization and authentication | 1 | 8 | 4 | MMR | Sprint Backlog (To do) | In Progress | Done | Impediments
Update a customer | 1 | 5 | 2.5 | EK | Robust authorization and authentication
Delete current account | 1 | 5 | 2.5 | LP | Update a customer
Setup Projects for collaboration | 1 | 5 | 2.5 | LJ | Delete current account
Log-In functionality | 1 | 3 | 1.5 | MMR | Setup Projects for collaboration
Create requirements document | 1 | 3 | 1.5 | EK | Log-In functionality
Log-in functionality web api | 1 | 2 | 1 | LP | Create requirements document
View Admin homepage | 2 | 5 | 2.5 | LJ | Log-in functionality web api
Delete savings customer | 2 | 5 | 2.5 | MMR | View Admin homepage
Accessibility with text to speech | 2 | 3 | 1.5 | EK | Create ERD Diagram
Create ERD Diagram | 2 | 3 | 1.5 | LP | Delete a customer
Delete a customer | 2 | 1 | 0.5 | LJ | View Bank Staff homepage
Open current account | 3 | 8 | 4 | MMR | Setting up REST API endpoints
Setting up REST API endpoints | 3 | 5 | 2.5 | EK | Make Entity Framework sample data
Confidentiality for access to system information | 3 | 5 | 2.5 | LP | Open current account
View Bank Staff homepage | 3 | 3 | 1.5 | LJ | Deposit functionality
Deposit functionality | 3 | 3 | 1.5 | MMR | Add a new user
Make Entity Framework sample data | 3 | 3 | 1.5 | EK | UI Design & Wireframes
Smooth & efficient user experience | 3 | 3 | 1.5 | LP | Open savings account
Add a new user | 4 | 8 | 4 | LJ | View Customer homepage
UI Design & Wireframes | 4 | 5 | 2.5 | MMR | Delete user
Open savings account | 4 | 5 | 2.5 | EK | Update user details
View Customer homepage | 4 | 3 | 1.5 | LP | Withdraw functionality
Withdraw functionality | 4 | 3 | 1.5 | LJ | View user details
Update user details | 4 | 3 | 1.5 | MMR | View list of users
Delete user | 4 | 2 | 1 | EK
View user details | 4 | 2 | 1 | LP | Add new customer
View list of users | 4 | 2 | 1 | LJ | Update account details
View transactions made | 5 | 5 | 2.5 | MMR | Add new customer
Add new customer | 5 | 3 | 1.5 | EK | View my transaction history
Update account details | 5 | 3 | 1.5 | LP | View customer details
View my transaction history | 5 | 3 | 1.5 | LJ | View List of Accounts
View customer details | 5 | 2 | 1 | MMR | View account details
View List of Accounts | 5 | 2 | 1 | EK | View List of my accounts
View account details | 5 | 2 | 1 | LP | View details of my account
View List of my accounts | 5 | 2 | 1 | LJ | View List of customers
View details of my account | 5 | 2 | 1 | MMR | View balance
View total of my bank balance | 5 | 2 | 1 | EK
View List of customers | 5 | 1 | 0.5 | LP
View balance | 5 | 1 | 0.5 | LJ

## 9. Scrum Ceremonies
Sprint Planning:
|  | Initial Sprint Planning Meeting | Tasks | Completion Date
|  |  | Define overall goals for the project and assign roles | 2024-06-05 |  | Sprint Planning Meetings | Tasks | Sprint 1 | Sprint 2 | Sprint 3
|  | Timebox: 8h | Define team rules and scrum values | 2024-06-05 |  |  | Create sprint backlog (8.Project Plan) | Completion Date: | Completion Date: | Completion Date:
|  | Actual time: 6h 45m | Create product vision | 2024-06-05 |  | Timebox: 8h | Define order of priority for tasks | 2024-06-14 | 2024-07-05 | 2024-07-19
|  |  | Define measure of success | 2024-06-05 |  |  | Use bucket sizing technique to determine story points | Time Taken: 6h 35m | Time Taken: 5h 45m | Time Taken: 6h 20m
|  |  | Determine team velocity and sprint backlog | 2024-06-06 |  |  | Determine type of task (functional/non-functional) | Sprint 1 Goal: | Sprint 2 Goal: | Sprint 3 Goal:
|  |  | Create visioning artefacts (Use case, process and UI Flow diagrams) | 2024-06-07 |  |  | Determine team velocity and total backlog story points | Produce a minimum Viable Product for MELLBank by Implementing Core features (Customer actions, basic transactions and Account Management) | Implement a notification system where users can receive notifications when transactions are made in their respective accounts | Refine transaction functionalities and apply different interest rates for different types of bank accounts
|  |  | Create personas | 2024-06-07 |  |  | Assign tasks to developers
|  |  | Define user stories | 2024-06-07 |  |  | Create Sprint goals
|  |  | Create the product backlog | 2024-06-07
|  |  | Create project plan | 2024-06-07
|  |  | Create definition of done | 2024-06-05
Daily Scrums (Sprint 1):
|  | Team Member | Daily Scrum Questions | Monday (17/06/2024) | Tuesday | Wednesday | Thursday | Friday
|  |  | What did you do yesterday? | - | ERD and sample data for savings account entity | Wireframes & EF Code 1st | REST API and Angular Front End
|  | MMR | What are you doing today? | ERD and sample data for savings account entity | Wireframes & EF Code 1st | REST API and Angular Front End
|  |  | Any impediments? | None | feeling ill | feeling ill and some network issues
None
|  |  | What did you do yesterday? |  | ERD and sample data for transaction entity, account | Update ERD, EF Code 1st & Naming Angular Components on Wireframes | REST API and Angular Front End
|  | LP | What are you doing today? | ERD and sample data for transaction entity | Update ERD, EF Code 1st & Naming Angular Components on Wireframes | REST API and Angular Front End | view my transactions and my transactions details, then front end and tests
|  |  | Any impediments? | None | None | None | None
|  |  | What did you do yesterday? | - | ERD and sample data for customer and message | Update ERD, EF Code 1st & Labelling Components on Wireframes | REST API and Angular Front End
|  | EK | What are you doing today? | ERD and sample data for customer and message | Update ERD, EF Code 1st & Labelling Components on Wireframes | REST API and Angular Front End | Admin Register Customer, admin seeing list of customers, update, deleted. Tests
|  |  | Any impediments? | None | None | Loadshedding
None (loadshedding might happen)
|  |  | What did you do yesterday? | - | ERD and sample data for current account entity | Wireframes & EF Code 1st | REST API and Angular Front End
|  | LJ | What are you doing today? | ERD and sample data for current account entity | Wireframes & EF Code 1st | REST API and Angular Front End | REST API and Front End for current account, open/close account and Tests
|  |  | Any impediments? | Network issue & feeling ill | feeling ill | None | None
Sprint 1 Day 1
ID | Priority | Developer | Sprint Backlog (To do) Task | InProgress | Done
1 | 1 | Elias |  |  | Setup Projects for collaboration
2 | 1 | Elias |  |  | Create EFCODE1ST project and add necessary NuGet packages
3 | 1 | Elias |  |  | Create REST API, Test Project, Log4net and add necessary NuGet packages
4 | 1 | Elias |  |  | Implement IdentityHelper service
5 | 1 | Elias |  |  | Create Angular project and setup basic project structure
6 | 1 | Elias |  |  | In Angular, add guards and modules for user roles
7 | 1 | Elias |  |  | Create ERD Diagram & Make Entity Framework sample data
8 | 2 | MELL |  |  | EF: Create Interest rate & Savings account classes and add sample data
9 | 2 | Michelle |  |  | EF: Create Customer & Message class and add sample data
10 | 2 | Elias |  |  | EF: Create Transaction class and add sample data
11 | 2 | Lerato |  |  | EF: Create Current account class and add sample data
12 | 2 | Luthando |  |  | Log-in functionality in rest api
Sprint 1 Day 2
ID | Priority | Developer | Sprint Backlog (To do) Task | InProgress | Done
13 | 3 | Lerato & Elias |  |  | Update ERD and EF Code1st Project
14 | 3 | MELL |  |  | Adjusting the Sample Data In EF Code1st Project
15 | 4 | Michelle & Luthando |  |  | UI Design & Wireframes
16 | 4 | Michelle |  |  | Wireframes for customer home pages
17 | 4 | Michelle |  |  | Wireframes for bank staff home pages
18 | 4 | Luthando |  |  | Wireframes for transaction and account management
19 | 4 | Luthando |  |  | Wireframes for admin cusomer managment
20 | 5 | Elias |  |  | Add Labels to all Wireframes
21 | 6 | Lerato |  |  | Naming all Components in Wireframes for Angular Project
Sprint 1 Day 3
ID | Priority | Developer | Sprint Backlog (To do) Task | InProgress | Done
21 | 1 | MELL | Writing REST API Endpoints and Angular Components |  | Writing REST API Endpoints and Angular Components
22 | 1 | MELL |  |  | Setup basic REST API Endpoints and basic Front End
23 | 1 | Luthando |  |  | Angular: Landing Page
22 | 4 | Luthando |  |  | Angular: Admin Homepage
23 | 5 | Luthando |  | Angular: Bank Staff Homepage
24 | 2 | Luthando |  |  | Angular: Customer Homepage
25 | 4 | Elias |  |  | Customer Management
26 | 4 | Elias |  |  | REST API: Add Customer controller
27 | 4 | Elias |  |  | REST API: Implement get customers and get customer by id
28 | 4 | Elias |  |  | REST API: Implement register customer endpoint
29 | 4 | Elias |  |  | REST API: Implement update and delete customer
30 | 5 | Elias |  |  | Angular: Create the authentication service
31 | 5 | Elias |  |  | Angular: Create Login page
32 |  | Elias |  |  | Angular: Refactor the footer and header off the landing page
33 | 7 | Michelle |  |  | Account Management
34 | 8 | Luthando |  | Open current account
35 | 9 | Michelle |  |  | REST API: Open savings account
36 | 9 | Michelle |  |  | REST API: Close savings account
37 | 9 | Michelle |  |  | REST API: Get all savings accounts for customer
38 | 9 | Michelle |  |  | REST API: Get savings account details
39 | 10 | Michelle |  | Angular: Mange accounts in staff home
40 | 10 | Michelle |  |  | Angular: View all savings accounts for customer
41 | 6 | Lerato |  |  | REST API: Transaction Management end points
42 | 6 | Lerato |  |  | REST API: Create a Deposit Money Endpoint
43 | 7 | Lerato |  |  | Angular: Create the transaction service
44 | 7 | Lerato |  |  | Angular: Implement the deposit method
45 | 7 | Lerato |  |  | Angular: Create the deposit page
46 | 8 | Lerato |  |  | Angular: Create withdraw page
47 | 8 | Lerato |  |  | REST API: Get all transactions
48 | 8 | Lerato |  | REST API: Get transaction details
49 | 8 | Lerato |  | REST API: View my transactions
50 | 8 | Lerato |  | REST API: View my transaction details
53 |  |  | About page, Service page, contact page
Sprint 1 Day 4
ID | Priority | Developer | Sprint Backlog (To do) Task | InProgress | Done
54 |  | Lerato
55 | 1 | MELL |  |  | Writing REST API Endpoints and Angular Components
56 | 1 | MELL |  |  | Setup basic REST API Endpoints and basic Front End
57 | 1 | Luthando |  |  | Angular: Landing Page
58 | 4 | Luthando |  |  | Angular: Admin Homepage
59 | 5 | Luthando |  |  | Angular: Bank Staff Homepage
60 | 2 | Luthando |  |  | Angular: Customer Homepage
61 | 4 | Elias |  |  | Customer Management
62 | 4 | Elias |  |  | REST API: Add Customer controller
63 | 4 | Elias |  |  | REST API: Implement get customers and get customer by id
64 | 4 | Elias |  |  | REST API: Implement register customer endpoint
65 | 4 | Elias |  |  | REST API: Implement update and delete customer
66 | 5 | Elias |  |  | Angular: Create the authentication service
67 | 5 | Elias |  |  | Angular: Create Login page
68 | 5 | Elias |  |  | Implement the customer account's list on customer home page
69 | 6 | Elias |  |  | Angular: Refactor the footer and header off the landing page
70 | 7 | Michelle |  |  | Account Management
71 | 8 | Luthando |  |  | Open current account
72 | 9 | Michelle |  |  | REST API: Open savings account
73 | 9 | Michelle |  |  | REST API: Close savings account
74 | 9 | Michelle |  |  | REST API: Get all savings accounts for customer
75 | 9 | Michelle |  |  | REST API: Get savings account details
76 | 10 | Michelle |  |  | Angular: Mange accounts in staff home
77 | 10 | Michelle |  |  | Angular: View all savings accounts for customer
78 |  | Michelle |  |  | REST API: close savings account
79 | 6 | Lerato |  |  | REST API: Transaction Management end points
80 | 6 | Lerato |  |  | REST API: Create a Deposit Money Endpoint
81 | 7 | Lerato |  |  | Angular: Create the transaction service
82 | 7 | Lerato |  |  | Angular: Implement the deposit method
83 | 7 | Lerato |  |  | Angular: Create the deposit page
84 | 8 | Lerato |  |  | Angular: Create withdraw page
85 | 8 | Lerato |  |  | REST API: Get all transactions
86 | 8 | Lerato |  |  | REST API: Get transaction details
87 | 8 | Lerato |  |  | REST API: View my transactions
88 | 8 | Lerato |  |  | REST API: View my transaction details
89 | 9 | Luthando |  |  | REST API: Current Account endpoints
90 | 7 | Lerato |  |  | Angular: View Transactions
91 | 10 | Lerato |  |  | Adapter Design Pattern
92
93
94
95
96
Sprint Review:
Feedback
Sprint Review Meeting (10/06/2024)
Timebox: 4h
Actual time: 2h 30m
Attendees:
Michelle
Elias
Lerato
Luthando
Sprint Retrospective:
Positives
Sprint Retrospective 1
Date Completed: 13/06/2024
Timebox: 2h
Actual time: 1h 45m
Future Improvements
Positives
Sprint Retrospective 2
Date Completed: 04/08/2023
Timebox: 2h
Actual time: 1h
Future Improvements
Positives
Sprint Retrospective 3
Date Completed: 18/08/2023
Timebox: 2h
Actual time: 2h
Future Improvements

## 10. Burndown
[6 empty] | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Sprints | Start | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Day | Points remaining | Day | Points remaining | Day | Points remaining | Day | Points remaining
Ideal Velocity | 24 | 24 | 24 | 24 | 24 | 1 | 24 | 1 | 24 | 1 | 24 | 1 | 24
Actual Velocity | 24 | 22 | 23 | 23 | 10 | 2 | 20 | 2 | 23 | 2 | 22 | 2 | 17
Remaining | 30 | 20 | 17 | 8 | 0 | 3 | 17 | 3 | 21 | 3 | 19 | 3 | 15
Projected | 30 | 20 | 17 | 8 | 0 | 4 | 15 | 4 | 15 | 4 | 16 | 4 | 11
[6 empty] | 5 | 11 | 5 | 14 | 5 | 13 | 5 | 10
[6 empty] | 6 | 9 | 5 | 10 | 6 | 10 | 5 | 9
[6 empty] | 7 | 8 | 5 | 7 | 7 | 7 | 5 | 5
[6 empty] | 8 | 5 | 5 | 5 | 8 | 5 | 5 | 1
[6 empty] | 9 | 3 | 5 | 3 | 9 | 4 | 5 | 0
[6 empty] | 10 | 2 | 5 | 1 | 10 | 1 | 5 | 0

## 11. ERD
Entity Relationship Diagram

## 12.1 Admin Wireframe
ID | Auth | Component name | Component selector | Description
A | Yes | AdminHome |  | Admin home page
B |  | Admin Panel
C |  | Footer |  | footer for all pages
D |  | ManageAccounts
E |  | RegisterCustomer
F |  | ViewTransaction
G |  | ManageUsers
H |  | Header
[5 empty] | ID | Auth | Component name
[5 empty] | A | Yes | TransactionsDetails
[5 empty] | B |  | Admin Panel
[5 empty] | C |  | Footer
[5 empty] | D |  | TransactionsDetails
[5 empty] | H |  | Header
[5 empty] | ID | Auth | Component name
[5 empty] | A | Yes | AccountDetails
[5 empty] | B |  | Admin Panel
[5 empty] | C |  | Footer
[5 empty] | D |  | AccountDetails
[5 empty] | H |  | Header
[5 empty] | ID | Auth | Component name
[5 empty] | A | Yes | RegisterCustomer
[5 empty] | B |  | Admin Panel
[5 empty] | C |  | Footer
[5 empty] | H |  | Header

## 12.2 BankStaff Wireframe
| ID | Auth | Component name
| A | Yes | StaffHome
| B |  | Logo
| C |  | Footer
| D |  | ManageAccounts
| E |  | ManageCustomers
| F |  | ViewTransactions
| H |  | Header
| ID | Auth | Component name
| A | Yes | TransactionsList
| B |  | Logo
| C |  | Footer
| H |  | Header
| ID | Auth | Component name
| A | Yes | TransactionsDetails
| B |  | Logo
| C |  | Footer
| H |  | Header
| ID | Auth | Component name
| A | Yes | AccountDetails
| B |  | Logo
| C |  | Footer
| H |  | Header
| ID | Auth | Component name
| A | Yes | AccountDetails
| B |  | Logo
| C |  | Footer
| D |  | AccountInfo
| H |  | Header
Customer Register Page
| ID | Auth | Component name
| A | Yes | RegisterCustomer
| B |  | Logo
| C |  | Footer
| H |  | Header
Customer List Page
| ID | Auth | Component name
| A | Yes | CustomerList
| B |  | Logo
| C |  | Footer
| H |  | Header
Customer Update Page
| ID | Auth | Component name
| A | Yes | UpdateCustomer
| B |  | Logo
| C |  | Footer
| H |  | Header

## 12.3 Customer Wireframe
ID | Auth | Component name | Description
A | Yes | CustomerHome | Customer home page
B |  | Logo
C |  | Footer | footer for all pages
D |  | CardImage
E |  | Transactions
H |  | Header
ID | Auth | Component name | Description
A |  | CustomerTransaction | Customer transaction page
B |  | Logo
C |  | Footer | footer for all pages
D |  | Transactions
E |  | CardImage
F |  | BalanceInfo
H |  | Header
ID | Auth | Component name | Description
A |  | Deposit
B |  | Logo
C |  | Footer
E |  | CardImage
F |  | BalanceInfo
H |  | Header
ID | Auth | Component name | Description
A |  | Withdraw
B |  | Logo
C |  | Footer
E |  | CardImage
F |  | BalanceInfo
H |  | Header

## 13. Lesson Learned
Lesson Learned
Team | Lesson
Michelle | Handling pressure helped me prioritize tasks, manage resources effectively, and stay focused on our goals.
Elias | Adapting to unexpected challenges improved my problem-solving skills and resilience as a team
Lerato | Communication kept me aligned and efficient, especially under tight deadlines.
Luthando | Agile Project Management taught me the importance of adaptability, continuous improvement, and team collaboration.The use scrum and agile methodology enhanced my ability to deliver my work to my group quickly and efficiently. Maintaining clear communication, and fostering a culture of teamwork were key to achieving group project goals and meeting deadline expectations effectively