## APM Delegation
ID | User | Tasks | Priority | Status
1 | MellBank Team | 1. Team | 1 | Done
2 | MellBank Team | 2. Product Vision | 2 | Done
3 | MellBank Team | 3. Measures of Success | 3 | Done
4 | MellBank Team | 4. Stakeholder Diagram | 4 | Done
5 | MellBank Team | 7. Velocity and Sprint Backlog | 7 | Done
6 | MMR | 5.1 Use Case Diagram | 5 | Done
7 | MMR | 6.1 User Stories | 6 | Done
8 | LP | 5.3 UI Flow Diagram | 5 | Done
9 | LP | 08. Project Plan | 8 | Done
10 | EK | 6.2 Product Backlog | 6 | Done
11 | EK | 09. Scrum Ceremonies | 9 | Done
12 | LJ | 5.2 Process Diagram | 5 | Done
13 | LJ | 10. Burndown | 10 | Done

## Sprint Delegation
ID | Priority | Users | Tasks | Status
1 | 1 | Elias | Setup Projects for collaboration | Done
2 | 1 | Elias | Create EFCODE1ST project and add necessary NuGet packages | Done
3 | 1 | Elias | Create REST API, Test Project, Log4net and add necessary NuGet packages | Done
4 | 1 | Elias | Implement IdentityHelper service | Done
5 | 1 | Elias | Log-in functionality in rest api | Done
6 | 1 | Elias | Create Angular project and setup basic project structure | Done
7 | 1 | Elias | In Angular, add guards and modules for user roles | Done
8 | 2 | MELL | Create ERD Diagram & Make Entity Framework sample data | Done
9 | 2 | Michelle | EF: Create Interest rate & Savings account classes and add sample data | Done
10 | 2 | Elias | EF: Create Customer & Message class and add sample data | Done
11 | 2 | Lerato | EF: Create Transaction class and add sample data | Done
12 | 2 | Luthando | EF: Create Current account class and add sample data | Done
13 | 3 | Lerato & Elias | Update ERD and EF Code1st Project | Done
14 | 3 | MELL | Adjusting the Sample Data In EF Code1st Project | Done
15 | 4 | Michelle & Luthando | UI Design & Wireframes | Done
16 | 4 | Michelle | Wireframes for customer home pages | Done
17 | 4 | Michelle | Wireframes for bank staff home pages | Done
18 | 4 | Luthando | Wireframes for transaction and account management | Done
19 | 4 | Luthando | Wireframes for admin cusomer managment | Done
20 | 4 | Elias | Add Labels to all Wireframes | Done
21 | 4 | Lerato | Naming all Components in Wireframes for Angular Project | Done
ID | Priority | Users | Tasks | Status
21 | 1 | MELL | Writing REST API Endpoints and Angular Components | Done
22 | 1 | MELL | Setup basic REST API Endpoints and basic Front End | Done
23 | 1 | Luthando | Angular: Landing Page | Done
22 | 4 | Luthando | Angular: Admin Homepage | Done
23 | 5 | Luthando | Angular: Bank Staff Homepage | Done
24 | 2 | Luthando | Angular: Customer Homepage | Done
25 | 4 | Elias | Customer Management | Done
26 | 4 | Elias | REST API: Add Customer controller | Done | Add extra rows if you need to elaborate
27 | 4 | Elias | REST API: Implement get customers and get customer by id | Done
28 | 4 | Elias | REST API: Implement register customer endpoint | Done
29 | 4 | Elias | REST API: Implement update and delete customer | Done
30 | 5 | Elias | Angular: Create the authentication service | Done
31 | 5 | Elias | Angular: Create Login page | Done
32 |  | Elias | Angular: Refactor the footer and header off the landing page | Done
33 | 7 | Michelle | Account Management | Done
34 | 8 | Luthando | Open current account | Done
35 | 9 | Michelle | REST API: Open savings account | Done
36 | 9 | Michelle | REST API: Close savings account | Done
37 | 9 | Michelle | REST API: Get all savings accounts for customer | Done
38 | 9 | Michelle | REST API: Get savings account details | Done
39 | 10 | Michelle | Angular: Mange accounts in staff home | Done
40 | 10 | Michelle | Angular: View all savings accounts for customer | Done
|  | Michelle | REST API: close savings account | Done
41 | 6 | Lerato | REST API: Transaction Management end points | Done
42 | 6 | Lerato | REST API: Create a Deposit Money Endpoint | Done
43 | 7 | Lerato | Angular: Create the transaction service | Done
44 | 7 | Lerato | Angular: Implement the deposit method | Done
45 | 7 | Lerato | Angular: Create the deposit page | Done
46 | 8 | Lerato | Angular: Create withdraw page | Done
47 | 8 | Lerato | REST API: Get all transactions | Done
48 | 8 | Lerato | REST API: Get transaction details | Done
49 | 8 | Lerato | REST API: View my transactions | Done
50 | 8 | Lerato | REST API: View my transaction details | Done
39 |  | Luthando | REST API: Current Account emdpoints | Done
40 |  | Lerato | Angular: View Transactions | Done
41 |  | Lerato | Adapter Design Pattern | Done
42 |  | Dev |  | Not Started
43 |  | Dev |  | Not Started
44 |  | Dev |  | Not Started
45 |  | Dev |  | Not Started
46 |  | Dev |  | Not Started
47 |  | Dev |  | Not Started
48 |  | Dev |  | Not Started
49 |  | Dev |  | Not Started
50 |  | Dev |  | Not Started
51 |  | Dev |  | Not Started
52 |  | Dev |  | Not Started
53 |  | Dev |  | Not Started

## Endpoints
MELL BANK
ID | User (BS-Bank Staff) | Auth (Y/N) | HTTP Method | Endpoints | Description
1 | - | N | POST | /api/ApplicationUser/Login | Logging into the system
2 | Admin,BS | Y | POST | /api/ApplicationUser/Register | Register an account into the system
3
4
5
6
7
8
9
10
11
12

## Project Names
Project names
Database Schema – Identity Database | MELLBank_AuthDB
Database Schema – EF Code First | MELLBank_EFDB
Data Access - Entity Framework Code First | MELLBank_EFCODE1ST
REST API - ASP.NET WEB API | MELLBank_RESTAPI
Front End Framework - Angular | MELLBank_ANG